## Impact Category
ISO PUBLIC
Select a Schedule Impact Category and Identify it for each project in the column labeled 'Reason for ISD Change from Original Comitted Date'. The Schedule Impact Definitions and Examples are listed below.
1 | Bundling Dependencies – Schedule impact due to bundling, scope tie-ins, or dependencies with other projects. This includes waiting on another project or benefiting from early completion, combined construction, or coordinated execution (e.g., proceeding early because Project X completed ahead of plan).
Delay example: Project cannot proceed until a dependent project is complete.
Acceleration example: Related project finishes early, enabling coordinated execution sooner.
2 | Clearances – Schedule impact related to meeting electrical or mechanical clearance requirements, including governing authority approvals (e.g., NERC, GO95/GO128, CAISO/WECC). This includes redesign, mitigation, or approval processes required to meet clearance standards.
Delay example: Redesign required to resolve clearance violations before construction can proceed.
Acceleration example: Clearance requirements are met without modification, allowing work to proceed as planned.
3 | Financing – Schedule impact driven by funding availability, approvals, cost recovery, or rate treatment timing. This includes delays in securing capital or benefits from early funding authorization.
Delay example: Capital approval is deferred to a future funding cycle.
Acceleration example: Funding is approved earlier than planned, enabling earlier project execution.
4 | ISO Action – Schedule impact resulting from CAISO actions, including approvals, re-studies, queuing outcomes, scope changes, or project prioritization decisions. This includes both delays and schedule pull-ins driven by ISO determinations.
Delay example: CAISO-required re-study extends the project schedule.
Acceleration example: CAISO approval is granted without requiring additional studies.
5 | Land Rights – Schedule impact related to land acquisition, easements, title issues, encroachments, access agreements, or eminent domain. This includes delays from negotiations or disputes and acceleration from early acquisition or agreements.
Delay example: Prolonged easement negotiations delay construction start.
Acceleration example: Land rights are secured early through negotiated agreements.
6 | Material – Schedule impact due to availability or delivery timing of project-specific materials not related to broader supply chain disruptions. This includes fabrication timing, procurement issues, or substitution with available materials.
Delay example: Late delivery of custom-fabricated equipment delays installation.
Acceleration example: Standard materials are used, allowing earlier installation.
7 | Other – Schedule impact that does not align with established categories and requires additional explanation in project documentation.
Delay example: Unique constraint not captured by standard categories delays the project.
Acceleration example: Innovative execution approach shortens the project duration.
8 | Outage – Schedule impact related to transmission or substation outage availability, constraints, or system conditions. This includes required outages for construction or energization activities.
Delay example: Required outage window is denied or postponed.
Acceleration example: An earlier or combined outage window becomes available.
9 | Permitting (CPUC/CEQA) – Schedule impact related to CPUC permitting and CEQA environmental review, including documentation, mitigation requirements, coordination, or litigation.
Delay example: Extended CEQA review or legal challenge delays approval.
Acceleration example: Permit is issued early with minimal conditions.
10 | Permitting (non-CPUC/CEQA) – Schedule impact related to federal, state, local, tribal, or special-district permits (e.g., BLM, USFS, city/county). This includes agency processing timelines and coordination requirements.
Delay example: Agency permit processing exceeds expected timelines.
Acceleration example: Required permits are issued ahead of schedule.
11 | Project Design – Schedule impact from engineering scope definition, design development, rework, constructability reviews, or changes outside the approved design.
Delay example: Late scope change requires redesign and delays construction.
Acceleration example: Reuse of previously approved designs shortens the design phase.
12 | Safety – Schedule impact related to safety incidents, compliance requirements, or work stoppages necessary to maintain safe working conditions.
Delay example: Work halted due to a safety incident investigation.
Acceleration example: Improved safety planning reduces downtime during construction.
13 | Securities – Schedule impact associated with financial instruments or structuring related to project funding and capital allocation.
Delay example: Delays in financial structuring postpone funding availability.
Acceleration example: Early completion of financing arrangements enables faster project start.
14 | Supply Chain Delays – Schedule impact driven by macro-level supply chain conditions such as global shortages, shipping congestion, or geopolitical factors affecting procurement timelines.
Delay example: Global shortages extend equipment lead times.
Acceleration example: Alternative sourcing reduces procurement duration.
15 | Unspecified – Schedule impact reported without a clearly defined or documented cause at the time of reporting.
Delay example: Milestone delay reported without explanation.
Acceleration example: Milestone achieved early without a documented reason.
16 | Vendor Quality / Delays – Schedule impact related to vendor or contractor performance, including QA/QC issues, rework, missed milestones, or strong execution performance.
Delay example: Vendor quality issues require rework and delay progress.
Acceleration example: Vendor exceeds milestone expectations and completes work early.
17 | Weather – Schedule impact related to environmental conditions such as severe weather, fire restrictions, access closures, or natural events that limit construction activities.
Delay example: Fire restrictions halt construction work.
Acceleration example: Favorable weather conditions allow extended work periods.
18 | Workforce Availability – Schedule impact related to labor availability, crew sizing, competing work demands, or specialized skill constraints.
Delay example: Crew shortages delay construction activities.
Acceleration example: Early crew mobilization improves productivity and schedule.

## PGaE
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
2526-R-02 | Ames 115 kV Short Circuit Mitigation | PG&E | 2025-2026 | 2029-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-12-01 | Initiating | TBD | 2028-12-01 | No Change | N/A | Q3-2026: New Addition
2425-R-02 | Ames Distribution – Palo Alto 115 kV transmission line | PG&E | 2025-2026 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-03-31 | In-Flight | TBD | 2030-02-21 | No Change | N/A | Q3-2026: Re-scoped in 2025-2026 CAISO Transmission Plan, Q1 2034 new Original ISD, Schedule/construction sequencing date adjustments.
2324-R-01 | Atlantic High Voltage Mitigation | PG&E | 2023-2024 | 2029-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-04-23 | 2028-04-05 | 2028-12-21 | 2029-05-01 | In-Flight | TBD | 2027-09-08 | Clearances | Utility | Q3-2026: Delay due to Schedule/construction sequencing date adjustment
2223-R-02 | Banta 60 kV Bus Voltage Conversion | PG&E | 2022-2023 | 2024-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2028-03-30 | 2027-12-10 | 2027-12-10 | 2028-01-20 | 2028-03-31 | In-Flight | N/A | 2024-10-28 | Permitting (Non-CPUC/CEQA) | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
1920-R-01 | Borden 230/70 kV Transformer Bank #1 Capacity Increase | PG&E | 2019-2020 | 2025-07-17 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2026-04-01 | 2026-04-01 | 2028-04-13 | 2028-05-30 | 2028-05-30 | 2029-03-30 | 2029-03-30 | In-Flight | TBD | 2027-12-01 | Financing | Utility | Q3-2026: No date changes at this time
2223-P-03 | Borden-Storey 230 kV 1 and 2 Line Reconductoring | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2029-05-01 | 2029-05-01 | 2030-05-01 | 2030-04-12 | 2029-05-08 | 2030-01-14 | 2030-05-01 | In-Flight | TBD | 2029-10-26 | Project Design | N/A | Q3-2026: Delay due to cable studies and site selection analysis. ISD within CAISO TPP Original ISD.
2324-R-02 | Camden 70 kV Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-03-19 | 2030-03-19 | In-Flight | TBD | 2028-07-27 | No Change | N/A | Q3-2026: No date changes at this time
1011-R-01 | Cascade 115/60 kV No.2 Transformer Project and Cascade - Benton 60 kV Line Project | PG&E | 2010-2011 | 2014-03-01 | 2023-12-01 | 2023-12-29 | 2024-12-13 | 2024-12-13 | 2024-12-31 | 2024-12-13 | 2024-12-13 | 2024-12-13 | 2025-07-11 | 2025-07-11 | 2025-06-13 | 2025-12-15 | 2025-12-15 | 2026-04-15 | 2026-04-26 | In-Service | N/A | 2019-07-09 | Financing | Utility | Q3-2026: In-service.
1819-R-01 | Christie-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2022-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-02-01 | 2028-02-01 | 2028-02-01 | 2028-02-01 | 2029-12-31 | 2029-09-17 | Initiating | NOC - TBD on Filing Date | 2029-06-15 | Financing | Utility | Q3-2026: Improved due to schedule/construction sequencing adjustments.
09-R-01 | Clear Lake 60 kV System Reinforcement | PG&E | 2009 | 2012-03-01 | 2027-02-01 | 2027-02-01 | 2027-02-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-07-01 | 2029-07-01 | 2029-07-01 | 2030-10-07 | 2030-10-07 | 2030-10-07 | 2030-10-07 | In-Flight | PTC - TBD on Filing Date | 2027-12-22 | Financing | Utility | Q3-2026: No date changes at this time
1718-R-01 | Coburn-Oil Fields 60 kV system project | PG&E | 2017-2018 | 2022-05-01 | 2029-06-01 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-21 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2029-06-26 | 2030-09-06 | 2031-09-05 | 2031-09-05 | 2032-08-30 | In flight | TBD | 2030-05-17 | Financing | Utility | Q3-2026: Delay due to recalibrated portfolio. Project to be kicked off in 2027
2122-P-03 | Collinsville 500/230 kV Substation Project | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-31 | 2027-12-31 | 2027-12-01 | 2028-05-01 | 2028-05-01 | 2028-05-30 | 2028-05-30 | In-Flight | NOC - Expected 2027 Q4 (plus LS Power CPCN) | 2027-06-01 | No Change | N/A | Q3-2026: No date changes at this time
2122-R-03 | Contra Costa PP 230 kV Line Terminals Reconfiguration Project | PG&E | 2021-2022 | 2025-05-01 | 2025-12-31 | 2025-12-31 | 2025-12-31 | 2025-07-07 | 2025-02-04 | 2025-05-30 | 2025-05-23 | 2025-05-22 | 2025-05-23 | 2025-05-23 | 2025-05-27 | 2025-09-15 | 2026-01-21 | 2026-02-27 | 2026-02-24 | In-Service | N/A | 2024-12-06 | Clearances | Utility | Q3-2026: In-service.
2122-R-05 | Coppermine 70 kV Reinforcement Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-13 | 2030-04-05 | 2030-04-05 | 2030-04-05 | In-Flight | TBD | 2027-01-04 | Material | Utility | Q3-2026: No date changes at this time
2324-R-03 | Cortina #1 60 kV Line Reconductoring | PG&E | 2023-2024 | 2028-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2028-02-28 | 2028-05-01 | 2028-03-17 | In-Flight | NOC: AL 7836-E Approved | 2026-10-06 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
2425-R-05 | Cortina #3 60 kV Reconductoring | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-05-01 | 2031-12-31 | 2031-12-31 | Initiating | TBD | 2029-07-13 | Workforce | Utility | Q3-2026: No date changes at this time
2122-R-06 | Cortina 230/115/60 kV Transformer Bank No. 1 Replacement Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2028-06-01 | 2028-06-01 | 2027-09-21 | 2027-10-13 | 2028-12-29 | 2028-01-06 | In-Flight | TBD | 2026-07-01 | Material | Utility | Q3-2026: Improved due to schedule/construction sequencing adjustments.
1819-R-02 | Cottonwood 115 kV Bus Sectionalizing Breaker | PG&E | 2018-2019 | 2022-12-31 | 2025-10-01 | 2025-10-02 | 2025-03-31 | 2024-12-24 | 2026-02-26 | 2026-02-26 | 2026-03-25 | 2025-11-12 | 2026-10-05 | 2026-06-19 | 2027-01-25 | 2028-02-24 | 2028-03-29 | 2028-08-25 | 2028-06-01 | In-Flight | N/A | 2027-01-22 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
1718-R-16 | Cottonwood 230/115 kV Transformers 1 and 4 Replacement | PG&E | 2017-2018 | 2019-11-01 | 2024-10-01 | 2024-10-02 | 2025-03-31 | 2025-02-14 | 2025-05-15 | 2025-08-11 | 2025-07-18 | 2025-11-19 | 2026-10-20 | 2026-10-20 | 2027-12-31 | 2028-10-20 | 2028-05-09 | 2028-10-06 | 2028-10-06 | In-Flight | N/A | 2026-11-16 | Financing | Utility | Q3-2026: No date changes at this time
2324-R-04 | Covelo 60 kV Voltage Support | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | 2030-05-01 | In-Flight | TBD | 2028-11-16 | No Change | N/A | Q3-2026: No date changes at this time
2324-R-05 | Crazy Horse Canyon - Salinas - Soledad #1 and #2 115 kV Line Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-04-23 | 2030-05-10 | In-Flight | TBD | 2029-08-16 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
2526-R-03 | DeAnza 115 kV Substation | PG&E | 2025-2026 | 2031-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-12-01 | On Hold (CAISO) | TBD | 2030-12-01 | No Change | N/A | Q3-2026: New Addition, Placed On Hold in 2025-2026 CAISO Transmission Plan
2324-R-06 | Diablo Canyon Area 230 kV High Voltage Mitigation | PG&E | 2023-2024 | 2027-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-07-25 | 2028-10-10 | 2030-04-30 | 2029-07-31 | In-Flight | TBD | 2027-11-10 | Other | Utility | Q3-2026: Improved due to determination of breaker type and shorter long lead material production.
2526-P-01 | Drum - Higgins 115 kV Line Reconductoring | PG&E | 2025-2026 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: New Addition
2425-P-01 | Eagle Rock- Fulton- Silverado 115 kV Line Reconductor | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2029-08-09 | 2029-04-28 | In-Flight | TBD | 2027-12-02 | No Change | N/A | Q3-2026: Improved due to project scoping. During scoping it was discovered that a portion of the existing conductor was sufficient ampacity. Also CAISO reduced capacity requiement on east/west section. Now only ~7mile reconductor.
1819-E-01 | East Marysville 115/60 kV Project | PG&E | 2025-2026 | 2030-01-30 | 2027-10-01 | 2027-11-10 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2028-01-17 | 2033-02-02 | 2029-07-17 | 2030-01-29 | 2030-01-29 | In-Flight | TBD | 2028-02-09 | Financing | Utility | Q3-2026: Re-scoped in 2025-2026 CAISO Transmission Plan, Jan 2030 new Original ISD. No date changes at this time
2526-P-02 | East Shore 230 kV Area Reinforcement | PG&E | 2025-2026 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | No Change | N/A | Q3-2026: New Addition
1920-R-02 | East Shore 230 kV Bus Terminals Reconfiguration | PG&E | 2019-2020 | 2024-12-31 | 2026-12-01 | 2026-12-31 | 2026-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2027-06-30 | 2027-05-06 | 2027-07-07 | N/A | N/A | Cancelled | TBD | N/A | No Change | N/A | Q3-2026: Cancelled in 2025-2026 CAISO Transmission Plan
2223-R-06 | Equipment Upgrade at CCSF Owned Warnerville 230 kV Substation | PG&E | 2022-2023 | 2024-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2024-12-31 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2023-04-28 | 2027-01-01 | 2027-01-01 | 2027-01-01 | In-Flight | N/A | 2026-08-01 | Other | Customer | Q3-2026: No date changes at this time
1314-R-06 | Estrella Substation Project | PG&E | 2013-2014 | 2019-05-01 | 2026-05-01 | 2026-05-27 | 2026-07-31 | 2026-07-31 | 2027-01-26 | 2028-05-30 | 2029-07-16 | 2029-07-16 | 2029-11-01 | 2029-07-05 | 2029-07-03 | 2029-03-30 | 2029-03-30 | 2029-03-30 | 2029-03-29 | In-Flight | PTC: A.17-01-023 Approved | 2025-11-03 | Permitting (CPUC/CEQA) | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
2324-R-09 | French Camp Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | 2030-05-01 | In-Flight | TBD | 2029-05-01 | Permitting (CPUC/CEQA) | Utility | Q3-2026: No date changes at this time
2223-R-07 | Garberville Area Reinforcement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2030-12-31 | 2030-12-31 | 2029-11-21 | 2027-12-28 | 2028-08-28 | 2028-12-07 | 2028-04-30 | In-Flight | N/A | 2026-07-06 | No Change | N/A | Q3-2026: Improved due to data error with 12/2028 in-service date
2223-R-07 | Garberville Area Reinforcement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2030-12-31 | 2030-12-31 | 2029-11-21 | 2027-12-28 | 2028-08-28 | 2028-12-07 | 2030-10-31 | In-Flight | NOC - Expected 2026 Q4 | 2027-06-08 | No Change | N/A | Q3-2026: Delay due to environmental reasons. Landslides were discovered in the area requiring additional geotechnical studies, risk evaluation, and re-design to mitigate risk. ISD within CAISO TPP Original ISD.
2324-R-10 | Gates 230/70 kV Transformer Addition | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | 2030-06-18 | In-Flight | TBD | 2028-06-27 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
1819-R-04 | Gold Hill 230/115 kV Transformer Addition Project | PG&E | 2018-2019 | 2022-12-31 | 2028-06-01 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2028-06-26 | 2030-04-12 | 2029-06-22 | 2030-01-07 | 2030-01-07 | 2030-01-07 | In-Flight | TBD | 2028-07-17 | Financing | Utility | Q3-2026: No date changes at this time
2425-R-07 | Gold Hill-El Dorado Reinforcement | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | 2032-05-01 | In-Flight | TBD | 2030-11-05 | No Change | N/A | Q3-2026: No date changes at this time
2425-R-08 | Greater Bay Area 500 kV Transmission Reinforcement | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2223-P-07 | Henrietta 230/115 kV Bank 3 Replacement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2027-06-01 | 2027-06-01 | 2028-07-21 | 2028-07-12 | 2028-10-02 | 2029-06-29 | 2029-06-29 | In-Flight | TBD | 2027-07-16 | No Change | N/A | Q3-2026: No date changes at this time
1718-R-03 | Herndon-Bullard 115 kV Reconductoring Project | PG&E | 2017-2018 | 2021-01-01 | 2026-12-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2027-12-31 | 2028-02-22 | 2028-02-22 | 2028-11-14 | In-Flight | NOC - Expected 2027 Q2 | 2028-02-24 | Financing | Utility | Q3-2026: Delay due to schedule/construction sequencing adjustments & Scope development
1718-R-15 | Ignacio Area Reinforcement | PG&E | 2017-2018 | 2023-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-06-26 | 2028-02-10 | 2029-01-03 | 2030-12-31 | 2030-12-31 | In-Flight | NOC - TBD on Filing Date | 2027-10-11 | Financing | Utility | Q3-2026: No date changes at this time
1819-R-05 | Jefferson 230 kV Bus Upgrade | PG&E | 2018-2019 | 2022-12-31 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-10-12 | 2026-11-06 | 2028-06-13 | 2028-06-26 | 2028-06-26 | In-Flight | TBD | 2027-12-10 | Financing | Utility | Q3-2026: No date changes at this time
2425-R-09 | Jefferson-Stanford 60 kV Recabling | PG&E | 2024-2025 | 2029-05-01 | 2026-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-05-01 | 2029-05-01 | 2029-05-01 | In-Flight | NOC - Expected 2026 Q3 | 2027-03-01 | No Change | N/A | Q3-2026: No date changes at this time
1112-R-10 | Kern PP 115 kV Area Reinforcement | PG&E | 2011-2012 | 2016-03-01 | 2027-08-01 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2027-08-09 | 2029-08-10 | 2029-08-10 | 2030-12-31 | 2029-08-10 | 2029-08-10 | 2029-08-23 | 2030-09-19 | In flight | NOC - Expected 2026 Q4 | 2028-01-10 | Financing | Utility | Q3-2026: Delay due to recalibrated portfolio. Project to be kicked off in 2027
2425-R-11 | Konocti – Eagle Rock 60 kV Line Reconductoring | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-31 | 2030-05-31 | In-Flight | TBD | 2029-12-20 | No Change | N/A | Q3-2026: No date changes at this time
1718-R-04 | Lakeville 60 kV Area Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | Initiating | NOC - TBD on Filing Date | 2028-02-01 | Financing | Utility | Q3-2026: No date changes at this time. PG&E is working with CAISO on Project Scope and is pending CAISO review and decision
2526-R-04 | Lincoln - Pleasant Grove Line Reconductoring | PG&E | 2025-2026 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: New Addition
1213-R-14 | Lockeford-Lodi Area 230 kV Development | PG&E | 2012-2013 | 2017-03-01 | 2027-06-01 | 2027-06-21 | 2028-12-29 | 2029-01-01 | 2029-01-01 | 2029-01-01 | 2029-01-11 | 2029-01-11 | 2029-06-08 | 2029-12-25 | 2029-12-10 | 2029-12-10 | 2029-12-10 | 2031-06-30 | 2031-06-30 | In-Flight | CPCN: A.23-09-001 Filed & Under Review | 2029-11-01 | Financing | Utility | Q3-2026: No date changes at this time
2223-R-08 | Lone Tree – Cayetano – Newark Corridor Series Compensation | PG&E | 2022-2023 | 2027-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-02 | 2027-10-13 | 2028-08-30 | 2028-08-30 | On Hold (CAISO) | TBD | 2028-04-17 | ISO Action | Utility | Q3-2026: Placed On Hold in 2025-2026 CAISO Transmission Plan
2223-R-09 | Los Banos 230 kV Circuit Breaker Replacement | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2029-12-04 | 2028-12-28 | 2028-12-28 | In-Flight | N/A | 2027-09-30 | No Change | N/A | Q3-2026: No date changes at this time
2223-R-10 | Los Banos 70 kV Area Reinforcement Project | PG&E | 2022-2023 | 2029-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-12-31 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2030-09-12 | 2030-08-27 | 2031-01-29 | 2031-01-29 | In-Flight | TBD | 2030-05-23 | Land Rights | Utility | Q3-2026: No date changes at this time
2526-R-05 | Los Esteros 230 kV Short Circuit Mitigation | PG&E | 2025-2026 | 2029-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-12-01 | Initiating | TBD | 2028-12-01 | No Change | N/A | Q3-2026: New Addition
2122-P-04 | Manning 500/230 kV Substation Project | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-12-01 | 2027-12-31 | 2027-12-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | In-Flight | NOC: AL 7706-E Approved | 2026-03-30 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
2122-R-08 | Manteca-Ripon-Riverbank-Melones Area 115 kV Line Reconductoring Project | PG&E | 2021-2022 | 2028-05-01 | 2028-12-31 | N/A | 2028-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-05-31 | 2029-02-02 | 2029-10-09 | 2029-10-09 | 2029-07-13 | 2027-09-30 | 2027-07-02 | In-Flight | TBD | 2026-05-11 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustment. ISD within CAISO TPP Original ISD.
2526-R-06 | Mariposa 70 kV Voltage Support | PG&E | 2025-2026 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-02 | No Change | N/A | Q3-2026: New Addition
1415-R-03 | Martin 230 kV Bus Extension | PG&E | 2014-2015 | 2021-12-01 | 2024-05-01 | 2024-05-24 | 2024-05-10 | 2024-05-24 | 2025-11-14 | 2025-11-13 | 2025-11-13 | 2026-04-23 | 2027-02-12 | 2028-10-13 | 2029-12-18 | 2029-10-17 | 2029-11-28 | 2028-10-27 | 2029-12-06 | In-Flight | CPCN: A.17-12-021 Approved | 2027-06-17 | Financing | Utility | Q3-2026: Delay due to scope development. Updated GIS commissioning duration received from Siemens resulted in delay in ISD.
2324-R-12 | Martin-Millbrae 60 kV Area Reinforcement | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-02-07 | 2030-05-01 | 2030-05-31 | In-Flight | TBD | 2028-02-25 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
2223-R-11 | Mesa Spare Transformer Installation | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-05-01 | 2028-04-01 | 2028-04-01 | 2029-04-01 | 2029-03-14 | 2029-08-23 | 2029-12-28 | 2031-06-17 | In-Flight | TBD | 2029-09-25 | No Change | N/A | Q3-2026: Delay due to scope development. PG&E is working with CAISO on Project Scope and is pending CAISO review and decision
2526-R-07 | Metcalf 230 kV Short Circuit Mitigation | PG&E | 2025-2026 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: New Addition
2223-R-12 | Metcalf 230/115 kV Transformers Circuit Breaker Addition | PG&E | 2022-2023 | 2026-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-30 | 2027-06-01 | 2027-06-01 | 2026-09-01 | 2027-06-23 | 2027-07-27 | N/A | N/A | Cancelled | TBD | N/A | No Change | N/A | Q3-2026: Cancelled in 2025-2026 CAISO Transmission Plan
2425-R-13 | Metcalf Substation 500/230 kV Transformer Bank Addition | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2425-R-14 | Metcalf-Piercy & Swift and Newark-Dixon Landing 115 kV Upgrade Re-scope | PG&E | 2024-2025 | 2028-05-01 | 2029-04-01 | 2029-04-01 | 2029-04-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-03-01 | 2027-03-01 | 2028-05-12 | 2030-04-04 | 2030-12-26 | 2030-12-26 | In-Flight | NOC - Expected 2027 Q2 | 2028-08-31 | ISO Action | Utility | Q3-2026: No date changes at this time
1314-R-13 | Midway – Kern PP #2 230 kV Line | PG&E | 2013-2014 | 2019-05-01 | 2024-06-01 | 2024-06-06 | 2025-07-03 | 2026-06-23 | 2026-06-23 | 2027-04-07 | 2027-04-07 | 2027-04-07 | 2027-04-29 | 2027-04-29 | 2028-12-31 | 2028-06-14 | 2028-06-14 | 2028-12-29 | 2028-12-29 | In-flight | NOC: AL 5026-E Approved | 2018-11-01 | Financing | Utility | Q3-2026: No date changes at this time
1314-R-13 | Midway – Kern PP #2 230 kV Line (Bakersfield-Kern Reconductor) | PG&E | 2013-2014 | 2019-05-01 | 2024-06-01 | 2024-06-06 | 2027-06-03 | 2027-09-01 | 2027-11-30 | 2028-02-25 | 2028-05-23 | 2028-08-21 | 2027-10-28 | 2028-01-24 | 2030-05-28 | 2030-09-30 | 2032-01-07 | 2032-01-07 | 2032-01-07 | In flight | NOC: AL 5924-E Approved | 2027-06-29 | Financing | Utility | Q3-2026: No date changes at this time
2526-R-08 | Midway 115 kV Bus Upgrade | PG&E | 2025-2026 | 2033-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2033-05-01 | Initiating | TBD | 2032-05-01 | No Change | N/A | Q3-2026: New Addition
1011-R-12 | Midway-Kern PP Nos. 1,3 and 4 230 kV Lines Capacity Increase (Kern PP 230 kV Area Reinforcement Project) | PG&E | 2010-2011 | 2013-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-05-30 | 2025-08-29 | 2025-08-29 | 2027-10-08 | 2030-08-22 | 2030-08-22 | 2030-02-01 | 2029-02-07 | 2029-02-07 | In-Flight | N/A | 2021-04-07 | Financing | Utility | Q3-2026: No date changes at this time
1213-R-19 | Midway-Temblor 115 kV Line Reconductor and Voltage Support | PG&E | 2012-2013 | 2018-05-01 | 2027-10-01 | 2027-10-20 | 2028-02-16 | 2028-05-16 | 2028-08-14 | 2028-11-09 | 2029-02-05 | 2029-04-06 | 2029-08-01 | 2029-10-26 | 2030-07-16 | 2029-02-15 | 2028-12-26 | 2029-02-01 | 2030-02-27 | In-Flight | NOC - Expected 2027 Q3 | 2027-10-18 | Project Design | Utility | Q3-2026: Delay due to Rescope of Tembler substation upgrade & clearance limitations
2526-R-09 | Monta Vista – Loyola – Los Altos 60 kV Line Reconductoring | PG&E | 2025-2026 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: New Addition
2526-R-10 | Monta Vista 230/115 kV Transformer Bank Addition | PG&E | 2025-2026 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-02 | No Change | N/A | Q3-2026: New Addition
1213-R-21 | Monte Vista 230 kV Bus Upgrade | PG&E | 2012-2013 | 2016-05-01 | 2024-08-01 | 2024-08-06 | 2024-07-17 | 2024-05-08 | 2025-07-04 | 2025-07-04 | 2025-07-04 | 2025-08-01 | 2025-08-07 | 2025-08-07 | 2025-09-23 | 2026-03-06 | 2026-03-04 | 2028-06-02 | 2028-05-30 | In-Flight | N/A | 2021-08-17 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
1920-R-04 | Moraga 230 kV Bus Upgrade | PG&E | 2019-2020 | 2024-12-31 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-05-01 | 2029-05-01 | 2029-05-01 | In-Flight | N/A | 2028-10-18 | Financing | Utility | Q3-2026: No date changes at this time
2425-R-15 | Moraga 230/115 kV Transformer Bank Addition | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-05-01 | 2031-05-01 | 2031-05-01 | Initiating | TBD | 2030-05-01 | No Change | N/A | Q3-2026: No date changes at this time
1819-R-06 | Moraga-Sobrante 115 kV Line Reconductor | PG&E | 2018-2019 | 2023-12-31 | On Hold | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | TBD | N/A | N/A | Cancelled | TBD | N/A | No Change | N/A | Q3-2026: Cancelled in 2025-2026 CAISO Transmission Plan
1314-R-17 | Morgan Hill Area Reinforcement (formerly Spring 230/115 kV substation) | PG&E | 2025-2026 | 2028-12-01 | 2026-04-01 | 2026-04-27 | 2026-04-28 | 2026-04-28 | 2026-04-28 | 2027-09-29 | 2027-09-29 | 2027-09-29 | 2029-01-30 | 2029-02-27 | 2028-12-28 | 2029-01-22 | 2028-12-26 | 2028-12-29 | 2028-12-29 | In-Flight | NOC - Expected 2026 Q3 | 2027-04-15 | No Change | N/A | Q3-2026: Re-scoped in 2025-2026 CAISO Transmission Plan, Dec 2028 new Original ISD, No date changes at this time
1314-R-18 | Mosher Transmission Project | PG&E | 2013-2014 | 2017-12-01 | 2027-12-01 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2027-12-15 | 2028-02-17 | 2028-11-17 | 2028-11-17 | 2029-05-31 | In-flight | NOC - TBD on Filing Date | 2027-07-01 | Financing | Utility | Q3-2026: Delay due to land right deficiency risk being triggered
2122-E-01 | Moss Landing – Las Aguilas 230 kV Series Reactor Project | PG&E | 2021-2022 | 2026-01-01 | 2026-12-31 | N/A | 2026-01-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2028-04-01 | 2028-04-01 | 2028-09-01 | 2028-09-01 | 2026-12-04 | 2027-08-25 | 2027-11-19 | In-Flight | TBD | 2027-07-14 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
2425-P-02 | New Helm 230/70 kV Bank #2 | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | N/A | N/A | Cancelled | TBD | N/A | No Change | N/A | Q3-2026: Cancelled in 2025-2026 CAISO Transmission Plan
2324-P-02 | New Humboldt 115/115 kV Phase Shifter with 115 kV line to Humboldt 115kV Substation | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2324-P-03 | New Humboldt 500 kV Substation with 500 kV line to Collinsville [HVDC operated as AC] | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2324-P-04 | New Humboldt to Fern Road 500 kV Line | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2526-R-11 | Newark 115 kV Short Circuit Mitigation | PG&E | 2025-2026 | 2029-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-12-01 | Initiating | TBD | 2028-12-01 | No Change | N/A | Q3-2026: New Addition
2526-R-12 | Newark 230/115 kV Bank Upgrade | PG&E | 2025-2026 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-02 | No Change | N/A | Q3-2026: New Addition
1920-R-05 | Newark 230/115 kV Transformer Bank #7 Circuit Breaker Addition | PG&E | 2019-2020 | 2024-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-15 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2029-02-20 | 2027-07-13 | 2027-07-13 | 2027-08-17 | In-Flight | TBD | 2027-07-12 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
1718-R-07 | Newark-Milpitas #1 115 kV Line Limiting Facility Upgrade | PG&E | 2017-2018 | 2019-06-01 | 2022-11-01 | 2022-11-01 | 2023-04-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-06-01 | 2025-06-01 | 2025-07-01 | 2027-05-06 | 2027-07-08 | 2026-12-04 | 2026-12-01 | In-Flight | TBD | 2026-08-11 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
2526-R-13 | Nortech 115 kV Short Circuit Mitigation | PG&E | 2025-2026 | 2029-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2029-12-01 | Initiating | TBD | 2028-12-01 | No Change | N/A | Q3-2026: New Addition
2324-P-05 | North Dublin -Vineyard 230 kV Reconductoring | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | 2034-05-01 | In-Flight | TBD | 2028-09-25 | No Change | N/A | Q3-2026: No date changes at this time
2223-R-15 | North East Kern 115 kV Line Reconductoring | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2033-12-31 | 2033-12-31 | 2032-12-31 | 2029-08-20 | 2031-12-01 | 2032-03-16 | 2032-03-16 | In-Flight | NOC - TBD on Filing Date | 2028-08-29 | Project Design | Utility | Q3-2026: No date changes at this time
2425-R-16 | North Oakland Reinforcement Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | 2032-05-01 | In-Flight | TBD | 2028-04-24 | No Change | N/A | Q3-2026: No date changes at this time
1112-R-15 | North Tower 115 kV Looping Project | PG&E | 2011-2012 | 2015-05-01 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-12-01 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2030-01-31 | 2028-02-01 | 2028-02-01 | 2029-02-01 | 2029-02-01 | 2029-02-01 | 2029-11-19 | 2030-03-20 | In-Flight | TBD | 2029-08-02 | Financing | Utility | Q3-2026: Delay due to scope development.
2526-P-03 | Oleum Area Reinforcement | PG&E | 2025-2026 | 2033-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2033-05-01 | Initiating | TBD | 2032-05-01 | No Change | N/A | Q3-2026: New Addition
1011-R-16 | Oro Loma 70 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2026-12-01 | 2026-12-16 | 2026-09-30 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2026-12-16 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2027-01-29 | 2028-08-28 | 2028-05-16 | 2028-05-23 | 2028-05-23 | In-Flight | NOC - Expected 2027 Q3 | 2027-09-24 | Financing | Utility | Q3-2026: No date changes at this time
1011-R-16 | Oro Loma 70kV Reinforcement Phase 2 | PG&E | 2025-2026 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | Initiating | TBD | 2031-05-01 | No Change | N/A | Q3-2026: Addition from Re-scope in 2025-2026 CAISO Transmission Plan
2223-R-16 | Panoche 115 kV Circuit Breaker Replacement and 230 kV Bus Upgrade project | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-31 | 2028-04-28 | 2028-06-01 | 2028-04-28 | 2028-03-31 | 2028-04-26 | 2028-04-28 | 2028-02-22 | In-Flight | TBD | 2026-07-01 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
2223-R-17 | Pittsburg 115 kV Bus Reactor project | PG&E | 2022-2023 | 2032-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2028-05-12 | 2028-05-12 | 2028-05-12 | 2028-05-30 | 2028-05-26 | 2028-05-26 | 2028-05-26 | In-Flight | NOC - Expected 2027 Q4 (plus LS Power CPCN) | 2027-06-29 | No Change | N/A | Q3-2026: No date changes at this time
07-R-02 | Pittsburg 230/115 kV Transformer Capacity Increase | PG&E | 2007 | 2011-05-01 | 2025-01-01 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2025-01-29 | 2026-06-17 | 2026-06-17 | 2026-09-04 | 2026-06-15 | 2028-05-09 | 2028-09-27 | 2029-01-31 | 2029-01-03 | 2029-01-23 | In-Flight | N/A | 2026-12-10 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
2425-R-17 | Pittsburg-Kirker 115 kV Line Section Limiting Elements Upgrade | PG&E | 2024-2025 | 2028-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-05-01 | 2028-05-01 | 2028-05-01 | Initiating | TBD | 2027-05-02 | No Change | N/A | Q3-2026: No date changes at this time
2122-P-05 | Reconductor Delevan-Cortina 230kV line | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-02-02 | 2028-08-16 | 2028-02-01 | 2028-02-29 | 2028-02-29 | 2028-02-28 | In-Flight | TBD | 2027-08-03 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
2425-P-03 | Reconductor of GWF – Kingsburg 115 kV line | PG&E | 2024-2025 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2122-P-06 | Reconductor Rio Oso–SPI Jct–Lincoln 115kV line | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-12-31 | 2030-02-01 | 2028-12-15 | In-Flight | TBD | 2028-10-04 | Project Design | Utility | Q3-2026: Improved due to schedule/construction sequencing adjustments.
1718-R-14 | Red Bluff-Coleman 60 kV Reinforcement | PG&E | 2017-2018 | 2021-12-01 | 2025-11-01 | 2025-11-19 | 2026-08-18 | 2026-08-18 | 2030-05-23 | 2031-11-19 | 2029-03-30 | 2028-11-07 | 2028-05-23 | 2029-03-06 | 2029-08-27 | 2029-03-28 | 2028-01-31 | 2028-03-20 | 2028-03-28 | In-Flight | NOC: AL 7766-E Approved | 2026-09-28 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
2223-R-18 | Redwood City Area 115 kV System Reinforcement | PG&E | 2022-2023 | 2030-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-12-01 | 2029-12-01 | 2029-12-01 | 2028-07-05 | 2030-03-14 | 2029-02-15 | 2030-02-13 | 2030-03-02 | In-Flight | NOC - TBD on Filing Date | 2028-11-08 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
2324-R-14 | Reedley 70 kV Capacity Increase | PG&E | 2023-2024 | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | 2030-05-01 | In-Flight | TBD | 2029-07-09 | No Change | CAISO | Q3-2026: No date changes at this time
2324-R-15 | Rio Oso - W. Sacramento Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2029-09-04 | 2029-09-06 | 2029-10-11 | In-Flight | TBD | 2029-04-13 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
1112-R-21 | Rio Oso Area 230 kV Voltage Support | PG&E | 2011-2012 | 2016-05-01 | 2024-10-01 | 2024-10-11 | 2024-10-31 | 2024-08-26 | 2024-12-09 | 2025-05-30 | 2025-06-04 | 2025-06-04 | 2025-06-19 | 2025-09-01 | 2026-05-14 | 2026-05-14 | 2026-10-15 | 2026-10-30 | 2026-10-30 | In-Flight | N/A | 2026-02-13 | Workforce | Utility | Q3-2026: No date changes at this time
1819-R-08 | Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | PG&E | 2018-2019 | 2024-12-31 | 2024-05-01 | 2024-05-06 | 2024-07-08 | 2024-08-16 | 2024-05-01 | 2024-06-03 | 2024-10-02 | 2024-11-21 | 2024-12-31 | 2024-12-31 | TBD | TBD | 2026-03-26 | 2026-05-26 | 2026-07-01 | In-Flight | N/A | 2023-02-15 | Other | Developer | Q3-2026: Schedule/construction sequencing date adjustments. Round Mountain & Table Mountain Series Capacitors to be operational in July 2027. This work can/will be completed post-energization of Fern Road.
2324-R-16 | Salinas Area Reinforcement | PG&E | 2023-2024 | TBD | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-12-01 | 2032-12-31 | 2032-12-31 | 2032-12-31 | In-Flight | TBD | 2027-11-19 | No Change | N/A | Q3-2026: No date changes at this time
2122-R-11 | San Jose Area HVDC 230 kV Line (Newark - NRS) | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-11-30 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | In-Flight | N/A | 2026-11-25 | No Change | N/A | Q3-2026: No date changes at this time
2122-R-10 | San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-06-28 | 2030-06-28 | 2030-06-28 | In-Flight | TBD | 2025-06-30 | No Change | N/A | Q3-2026: No date changes at this time
2122-R-10 | San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | PG&E | 2021-2022 | 2028-01-01 | 2028-12-31 | N/A | 2028-01-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-04-30 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | In-Flight | NOC: AL 7391-E Approved | 2026-01-04 | No Change | N/A | Q3-2026: No date changes at this time
2425-R-18 | San Jose B – NRS 230 kV line | PG&E | 2024-2025 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2526-R-14 | San Jose B 230/115 kV Transformer Bank Addition | PG&E | 2025-2026 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | Initiating | TBD | 2029-05-01 | No Change | N/A | Q3-2026: New Addition
2425-R-19 | San Mateo 230/115 kV Transformer Bank Addition Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | 2032-05-01 | Initiating | TBD | 2031-05-02 | No Change | N/A | Q3-2026: No date changes at this time
2425-R-20 | San Miguel New 70 kV Line | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | 2032-06-01 | In-Flight | TBD | 2032-01-08 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
2223-R-19 | Santa Rosa 115 kV lines Reconductoring project | PG&E | 2022-2023 | 2028-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2029-10-31 | 2032-05-21 | 2032-05-21 | 2032-05-21 | 2032-05-21 | Initiating | TBD | 2031-04-01 | Financing | Utility | Q3-2026: No date changes at this time
2526-R-15 | Saratoga-Vasona 230 kV Line Reconductoring | PG&E | 2025-2026 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: New Addition
2122-R-12 | Series Compensation on Los Esteros-Nortech 115 kV Line | PG&E | 2021-2022 | 2023-06-01 | 2023-12-31 | N/A | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2025-12-23 | 2025-12-23 | 2026-03-03 | 2025-12-30 | 2026-02-10 | 2026-04-23 | 2026-11-24 | In-Flight | TBD | 2026-02-23 | Financing | Utility | Q3-2026: Delay due to third party generator outages, which caused the required clearances to be canceled and rescheduled for the fall.
2425-R-24 | Sobrante 230 kV Bus Upgrade | PG&E | 2024-2025 | 2033-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2033-05-01 | 2033-05-01 | 2033-05-01 | In-Flight | TBD | 2029-04-12 | No Change | N/A | Q3-2026: No date changes at this time
2324-P-06 | Sobrante 230/115 kV Transformer Bank Addition | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2034-05-01 | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2223-R-21 | South Bay Area Limiting Elements Upgrade | PG&E | 2022-2023 | 2027-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2026-03-01 | 2026-03-01 | 2025-05-01 | 2026-04-10 | 2026-06-10 | 2026-07-29 | 2026-11-10 | In-Flight | N/A | 2024-06-01 | No Change | N/A | Q3-2026: Delay due to Schedule/construction sequencing date adjustment. ISD within CAISO TPP Original ISD.
2425-R-25 | South Bay Reinforcement Project | PG&E | 2025-2026 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-05-01 | 2032-05-01 | In-Flight | TBD | 2030-11-01 | No Change | N/A | Q3-2026: Re-scoped in 2025-2026 CAISO Transmission Plan, May 2032 new Original ISD, Part G placed On Hold in 2025-2026 CAISO Transmission Plan. Part G Scope: Swap the connections of the Newark-Trimble and Trimble-FMC 115 kV lines at the tower line. Additionally, rebuild the KRS-Trimble section using double 795 ACSS conductors over a length of approximately 3 miles. Improved due to project rebaselining upon kickoff
2526-R-16 | South Oakland Reinforcement (Phase 2) | PG&E | 2025-2026 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: New Addition
2425-R-26 | South Oakland Reinforcement Project | PG&E | 2024-2025 | 2032-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-05-01 | 2032-05-01 | 2032-05-03 | In-Flight | TBD | 2028-07-21 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
1819-R-09 | South of Mesa Upgrade | PG&E | 2018-2019 | 2023-12-31 | 2026-09-01 | 2026-09-03 | 2026-05-26 | 2026-05-26 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-15 | 2027-04-15 | 2031-03-10 | 2029-06-06 | 2029-06-06 | 2029-06-06 | 2029-09-01 | In-flight | NOC - Expected 2027 Q3 | 2027-07-09 | Financing | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
07-R-01 | South of San Mateo Capacity Increase | PG&E | 2007 | 2009-05-01 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2027-06-22 | 2028-12-01 | 2028-12-01 | 2027-10-29 | 2028-06-22 | 2029-02-21 | 2031-12-31 | 2031-12-31 | In-Flight | NOC - TBD on Filing Date | 2027-12-01 | Financing | Utility | Q3-2026: No date changes at this time
2122-R-13 | Table Mountain Second 500/230 kV Transformer | PG&E | 2021-2022 | 2027-01-01 | 2027-12-31 | N/A | 2027-01-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-06-01 | 2028-06-01 | 2026-09-28 | 2027-10-13 | 2029-05-09 | 2029-05-18 | 2029-05-18 | In-Flight | TBD | 2027-11-22 | Financing | Utility | Q3-2026: No date changes at this time
2324-R-17 | Tejon Area Reinforcement | PG&E | 2023-2024 | 2027-08-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-08-01 | 2028-08-30 | 2029-04-26 | 2030-04-30 | In-Flight | TBD | 2027-08-06 | Project Design | CAISO | Q3-2026: Delay due to scope development. Expanding substation scope at Tejon and San Bernard is driving ongoing design changes. Finalization of the T-Line design remains dependent on completion of substation scope definition.
2324-P-07 | Tesla - Newark 230 kV Line No. 2 Reconductoring | PG&E | 2023-2024 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | 2034-12-29 | 2034-12-29 | 2030-03-31 | In-Flight | TBD | 2028-03-07 | No Change | N/A | Q3-2026: Improve due to recalibrated portfolio.
2526-R-17 | Tesla – Trimble – Metcalf 230 kV Corridor Expansion | PG&E | 2025-2026 | 2034-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-05-01 | Initiating | TBD | 2033-05-01 | No Change | N/A | Q3-2026: New Addition
2223-R-23 | Tesla 115 kV Bus Reconfiguration Project | PG&E | 2022-2023 | 2030-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-12-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | 2028-06-01 | 2028-06-30 | 2028-06-30 | 2030-05-31 | In-Flight | TBD | 2028-04-20 | No Change | N/A | Q3-2026: Delay due to clearance limitation. Construction Clearance and Sequencing related delays, project can only get clearances 6 months from October to March period during winter months, no summer peak clearances is allowed. ISD within CAISO TPP Original ISD.
1718-R-11 | Tie line Phasor Measurement Units | PG&E | 2017-2018 | 2020-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2027-08-16 | 2027-08-16 | 2028-02-09 | 2028-02-09 | 2028-12-28 | 2027-12-01 | 2027-12-31 | 2027-12-31 | 2027-12-31 | In-Flight | N/A | 2024-05-13 | Financing | Utility | Q3-2026: No date changes at this time
2526-R-18 | Trimble 115 kV Short Circuit Mitigation | PG&E | 2025-2026 | 2034-12-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2034-12-01 | Initiating | TBD | 2033-12-01 | No Change | N/A | Q3-2026: New Addition
2223-R-24 | Tulucay-Napa #2 60 kV line Reconductoring project | PG&E | 2022-2023 | 2028-12-31 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028-12-01 | 2026-12-31 | 2026-12-31 | 2026-12-01 | 2027-07-23 | 2026-12-17 | 2026-12-14 | 2026-12-14 | In-Flight | NOC - Expected 2026 Q3 | 2026-12-02 | No Change | N/A | Q3-2026: No date changes at this time
1819-R-11 | Tyler 60 kV Shunt Capacitor | PG&E | 2018-2019 | 2022-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-03-01 | 2027-03-01 | 2027-09-20 | 2027-09-30 | 2028-01-05 | 2028-03-31 | 2028-03-31 | In-Flight | TBD | 2027-09-01 | Financing | Utility | Q3-2026: No date changes at this time
1718-R-17 | Vaca Dixon Area Reinforcement (INSTALL (2) CAPACITOR BANKS) | PG&E | 2017-2018 | 2023-12-01 | 2026-07-01 | 2026-07-10 | 2026-08-21 | 2025-08-18 | 2025-12-25 | 2025-12-30 | 2026-02-06 | 2026-02-06 | 2026-04-29 | 2027-04-12 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2028-06-30 | 2028-06-30 | In-Flight | PTC: A.24-06-008 Approved/NOC: AL 7542-E Approved | 2025-10-09 | Financing | Utility | Q3-2026: No date changes at this time
1718-R-13 | Vaca Dixon-Lakeville 230 kV Corridor Series Compensation | PG&E | 2017-2018 | 2019-10-01 | 2027-04-01 | 2027-04-01 | 2025-10-20 | 2025-10-20 | 2025-10-20 | 2026-05-08 | 2025-10-20 | 2025-10-20 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-11-18 | 2027-11-17 | 2027-11-17 | 2029-12-31 | In-flight | N/A | 2027-09-02 | Financing | Utility | Q3-2026: Delay due to Schedule/construction sequencing date adjustment after project being re-kicked off. Project was previously undergoing scope redevelopment with CAISO.
2324-R-18 | Vaca-Plainfield 60 kV Line Reconductoring | PG&E | 2023-2024 | 2030-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2030-05-01 | 2030-05-01 | 2030-05-01 | 2030-05-01 | Initiating | TBD | 2029-05-01 | No Change | N/A | Q3-2026: No date changes at this time
2122-R-14 | Vasona-Metcalf 230 kV Line Limiting Elements Removal Project | PG&E | 2021-2022 | 2025-05-01 | 2025-12-31 | N/A | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-05-01 | 2025-06-01 | 2025-06-01 | 2026-08-31 | 2026-07-27 | 2026-06-02 | 2027-04-06 | 2027-06-10 | In-Flight | TBD | 2026-01-20 | Bundling Dependency | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
1011-R-30 | Vierra 115 kV Looping Project | PG&E | 2010-2011 | 2014-05-01 | 2025-06-01 | 2025-06-23 | 2027-03-23 | 2025-07-31 | 2025-07-31 | 2025-07-31 | 2025-05-01 | 2026-05-29 | 2026-07-31 | 2027-05-06 | 2027-04-23 | 2027-05-10 | 2026-06-03 | 2026-06-24 | 2026-05-20 | In-Service | PTC: A.18-06-004 Approved | 2024-05-21 | Financing | Utility | Q3-2026: In-service.
2122-R-16 | Weber-Mormon Jct 60 kV Line Section Reconductoring Project | PG&E | 2021-2022 | 2027-05-01 | 2027-12-31 | N/A | 2027-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2027-05-31 | 2029-02-02 | 2027-12-06 | 2027-04-12 | 2027-05-13 | 2027-07-26 | 2027-06-16 | In-Flight | NOC: AL 7813-E Approved | 2027-01-05 | No Change | N/A | Q3-2026: Schedule/construction sequencing date adjustments.
2425-R-28 | West Fresno 115 kV Voltage Support | PG&E | 2024-2025 | 2031-05-01 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-05-01 | 2031-05-01 | 2031-05-01 | Initiating | TBD | 2030-05-01 | No Change | N/A | Q3-2026: No date changes at this time
1314-R-27 | Wheeler Ridge Junction Substation | PG&E | 2013-2014 | 2020-05-01 | On Hold | N/A | 2029-05-04 | 2029-05-04 | 2029-05-04 | 2032-10-11 | 2034-03-28 | 2034-03-28 | 2029-05-04 | 2033-12-31 | 2032-12-01 | 2033-07-11 | 2034-05-01 | 2034-05-19 | 2034-05-01 | In-Flight | NOC - Expected 2026 Q2 | 2030-03-07 | ISO Action | Utility | Q3-2026: Schedule/construction sequencing date adjustments.
#N/A | Willow Creek Voltage Support | PG&E | 2009 | 2011-03-01 | 2026-07-01 | 2026-07-01 | 2026-07-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-10-01 | 2027-10-01 | 2027-10-01 | 2027-11-22 | 2028-03-06 | 2028-03-06 | In-Flight | TBD | 2027-10-15 | Material | Utility | Q3-2026: No date changes at this time
1011-R-32 | Wilson 115 kV Area Reinforcement | PG&E | 2010-2011 | 2015-05-01 | 2026-09-01 | 2026-09-29 | 2027-08-12 | 2027-08-12 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2028-01-28 | 2029-08-16 | 2029-12-21 | 2030-05-02 | 2031-02-26 | In-Flight | N/A | 2028-05-24 | Financing | Utility | Q3-2026: Delay due to Schedule/construction sequencing date adjustment after project being re-kicked off & ongoing scope development
1920-R-09 | Wilson-Oro Loma 115kV Line Reconductoring | PG&E | 2019-2020 | 2026-12-31 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2027-05-01 | 2027-05-01 | 2027-05-01 | 2027-02-12 | 2028-07-03 | 2028-10-12 | In-Flight | NOC - TBD on Filing Date | 2027-12-29 | Project Design | Utility | Q3-2026: Delay due to Schedule/construction sequencing date adjustments.

## SCE
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
2223-P-18 | Serrano–Del Amo–Mesa 500 kV Transmission Reinforcement | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | 2033-12-31 | 2033-12-31 | 1933-12-01 | 2033-12-01 | 2033-12-01 | 1935-01-01 |  | Cancelled | 2027-02-01 | 2031-01-01 |  |  | July 2026: Project cancelled to be removed in future TDF.
2122-P-02 | Laguna Bell - Mesa No. 1 230 kV Line Rating Increase Project | SCE | 2021-2022 | 2023 | N/A | New | 2023-12-01 | 2023-12-01 | 2023-12-31 | 2024-04-01 | 2024-05-31 | 2024-05-01 | 2024-06-01 | 2024-06-01 | 2025-06-01 | Complete | 2025-04-02 | In Service |  | In Service | Exempt | 2024-05-02 |  |  | In-Service. Project will be removed in future TDF.
2324-R-13 | Mira Loma 500 kV Bus SCD Mitigation | SCE | 2023-2024 | 2027 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | 2026-12-01 | 2026-12-01 | 2025-01-31 |  | In Service | Exempt | 2026-03-01 |  |  | CB replacement cancelled in lieu of addition of TRV capacitance to affected units, project complete.
2425-R-01 | Alamitos 230 kV SCD Upgrade | SCE | 2024-2025 | 2032 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | 1932-06-01 | TBD | On Hold | Exempt | TBD | ISO Action | CAISO
09-R-03 | Alberhill 500 kV Method of Service | SCE | 2009 | 2014 | TBD | 2025-10-01 | 2025-10-01 | 2027-04-01 | 2027-04-30 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-10-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | 2029-12-01 | Engineering | 2009-09-01 | 2026-10-01 | No Change | N/A
2122-R-01 | Antelope 66 kV Short Circuit Duty Mitigation Project | SCE | 2021-2022 | 2026 | N/A | New | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2026-12-26 | 2026-12-26 | 2027-05-31 | Construction | Exempt | 2024-10-31 | Outage | Utility
2223-R-01 | Antelope-Whirlwind 500 kV Line Upgrade | SCE | 2022-2023 | 2025 | N/A | New | New | New | New | New | New | Pending | Pending | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2026-01-26 | 2026-01-26 | Construction Complete | Exempt | 2025-10-22 | No Change | N/A
2223-R-03 | Barre 230 kV Switchrack Conversion to BAAH Project | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | Pending | 2026-06-01 | 2026-06-30 | 2026-06-30 | 2026-06-30 | 2026-06-01 | 2026-06-01 | 2027-12-31 | 2027-12-31 | 2028-12-31 | Construction | Exempt | 2025-08-25 | Outage | Utility
2223-P-04 | Colorado River-Red Bluff 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-02-01 | 2027-12-01 | 2026-12-31 | 2027-04-01 | 2028-12-31 | Preliminary Engineering | Pending | 2027-11-01 | Outage | Utility
2122-R-07 | Devers 230 kV Reconfiguration Project | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2025-06-01 | 2027-06-01 | 2027-06-01 | 2027-04-13 | 2027-04-13 | 2027-05-20 | Construction | Exempt | 2024-06-17 | Other | Utility | July 2026: Slight shift by one month due internal logic of scheduling application processing completion of construction activities.
2526-R-20 | Devers 230 kV SCD Upgrade | SCE | 2025-2026 | 2035 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2035-12-31 | Initiation | Exempt | TBD | No Change | N/A
2223-P-05 | Devers-Red Bluff 500 kV 1 and 2 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 1930-03-01 | 1930-01-01 | 2030-12-31 | 2030-12-31 | 2032-12-31 | Preliminary Engineering | Pending | 2030-11-01 | Outage | Utility
2223-P-06 | Devers-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-04-01 | 2027-12-01 | 2028-04-28 | 2028-12-01 | 2030-12-31 | Preliminary Engineering | Pending | 2028-11-01 | Outage | Utility
2324-R-07 | Eldorado 230 kV Short Circuit Duty Mitigation Project | SCE | 2023-2024 | 2029 | N/A | New | New | New | New | New | New | New | New | New | Pending | Pending | 2029-12-01 | 2029-12-01 | 2029-12-01 | Engineering | Exempt | 2028-06-01 | No Change | N/A
2324-R-08 | Etiwanda 230 kV Bus SCD Mitigation | SCE | 2023-2024 | [15 empty] | 2030-12-31 | Final Engineering | Exempt | 2028-10-01 | No Change | N/A
2526-R-23 | Etiwanda and Mira Loma 230 kV SCD Upgrade | SCE | 2025-2026 | 2031 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | TBD | Initiation | Exempt | TBD | No Change | N/A
2324-R-11 | Inyo 230 kV Shunt Reactor | SCE | 2023-2024 | 2027 | N/A | New | New | New | New | New | New | Pending | N/A | N/A | 2027-12-31 | 2026-12-01 | 2026-09-25 | 2026-12-02 | 2026-12-31 | Engineering Design | Exempt | 2026-06-26 | No Change | N/A
2425-R-10 | Julian Hinds-Mirage 230 kV Advanced Reconductor | SCE | 2024-2025 | 2030 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | TBD | TBD | On Hold | Pending | TBD | ISO Action | CAISO
2425-R-12 | Kramer-Coolwater 115 kV Line Looping into Tortilla 115 kV Substation | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | TBD | TBD | On Hold | Pending | TBD | ISO Action | CAISO
1213-P-02 | Lugo – Eldorado series cap and terminal equipment upgrade | SCE | 2012-2013 | 2016 | 2022-06-01 | 2023-06-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2024-12-01 | 2025-05-01 | 2026-06-30 | 2026-06-30 | 2026-04-20 | Construction Complete | 2018-05-01 | 2020-11-02 | Other | N/A
1516-R-09 | Lugo – Victorville 500 kV Upgrade (SCE portion) | SCE | 2016-2017 | 2018-12-31 | 2023-06-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-01-31 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2026-01-01 | 2027-01-31 | 2027-01-01 | 2025-05-01 | 2025-12-30 | 2027-03-31 | 2027-03-01 | Construction | Exempt | 2019-01-01 | No Change | N/A
2526-R-19 | Lugo 230 kV CB Upgrade | SCE | 2025-2026 | 2031 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-07-31 | Initiation | Exempt | TBD | No Change | N/A
2526-R-21 | Lugo 500 kV Reactive Power Reinforcement | SCE | 2025-2026 | 2032 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2033-12-31 | Initiation | Pending | TBD | No Change | N/A | July 2026: Project completion date moved to December 2033 to account for multiple on-going projects at Lugo Substation in development through 2032 and to also account for additional time related to the EPC contract for the STATCOM.
08-R-01 | Lugo Substation Install new 500 kV CBs for AA Banks | SCE | 2008 | 2011-12-01 | 2024-12-01 | 2024-04-01 | 2024-04-01 | 2024-12-01 | 2025-12-31 | 2025-12-01 | 2025-12-01 | 2025-12-30 | 2025-12-01 | 2026-12-30 | 2029-12-01 | 2029-12-01 | 2031-06-30 | 2031-06-30 | 2032-06-29 | Preliminary Engineering | Exempt | 2031-01-02 | Bundling Dependency | N/A | July 2026: The first Lugo AA Bank will be replaced in 2030 following the completion of the Lugo 3AA Bank in 2029. Due to schedule work at Lugo in 2031 and the scheduled delivery date for the 500kV CB's for the remaining Lugo 3AA Bank, the completion date for the 2nd AA Bank was moved to 2032. However, SCE is currently evaulating the possibility of completion both AA Banks by the end of 2030 if the delivery date for the 2nd set of 500kV CB's are delivered at an earlier date.
1314-P-01 | Lugo-Mohave series capacitor upgrade | SCE | 2013-2014 | 2016 | 2022-06-01 | 2023-04-01 | 2023-06-01 | 2023-06-01 | 2023-12-31 | 2023-12-23 | 2023-12-23 | 2023-12-30 | 2024-06-01 | 2024-12-31 | 2025-04-01 | 2025-05-01 | 2026-06-30 | 2026-06-30 | 2026-04-30 | Construction Complete | 2018-05-01 | 2020-11-02 | Other | N/A
2223-P-09 | Lugo-Victor-Kramer Upgrade (1/3) Add 3rd Lugo 500/230 kV Transformer | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | 2028-12-01 | 2029-06-30 | 2029-06-30 | 2029-06-01 | Preliminary Engineering | Exempt | 2028-01-01 | No Change | N/A
2223-P-09 | Lugo-Victor-Kramer Upgrade (2/3) Reconductor Lugo–Victor 230 kV No. 1, 2, 3 & 4 lines using HTLS | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2028-12-01 | 2028-05-01 | 2026-12-20 | 2028-12-20 | 2028-12-31 | Engineering | Pending | 2027-10-01 | No Change | N/A | July 2026: Project was previosly paused by CAISO and was released from hold in Q2 2026, the ISD is currently being reevaluated and is expected to change.
2223-P-09 | Lugo-Victor-Kramer Upgrade (3/3) Rebuild/build Kramer–Victor 115 kV lines to 230 kV and Loop the old segment of Kramer–Victor 115 kV into Roadway | SCE | 2022-2023 | 2033 | N/A | New | New | New | New | New | New | Pending | Pending | 2033-06-30 | 2033-06-01 | 2033-06-01 | 2032-12-01 | 2032-09-01 | 2033-12-01 | Preliminary Engineering | 2028-07-01 | 2031-01-01 | ISO Action | CAISO
2526-R-22 | Mesa - Laguna Bell 230 kV #2 Upgrade | SCE | 2025-2026 | 2032 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2032-06-01 | Initiation | Exempt | 2031-01-01 | No Change | N/A
07-R-03 | Method of Service for Wildlife 230/66 kV Substation | SCE | 2007 | 2009 | 2026-10-01 | 2026-10-01 | 2026-10-01 | 2027-07-01 | 2027-07-31 | 2027-10-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | TBD | 2029-10-01 | 2029-10-01 | 2029-10-01 | 2029-10-01 | 2029-10-01 | Construction | 2015-04-01 | 2025-06-01 | No Change | N/A
2223-R-14 | Mira Loma 500 kV Circuit Breaker Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2028-12-01 | 2028-08-14 | 2028-08-14 | 2028-12-01 | 2028-08-14 | 2028-08-14 | 2028-08-14 | Engineering | Exempt | 2028-05-18 | No Change | N/A
2223-P-10 | Mira Loma-Mesa 500 kV Underground Third Cable | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2028-12-01 | 2026-12-01 | 2026-12-01 | 2026-12-01 | Construction | Exempt | 2026-07-01 | No Change | N/A
2223-R-05 | New Coolwater A 230/115 kV Bank | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | 2027-12-10 | 2027-12-10 | 2027-12-01 | 2027-04-01 | 2028-06-02 | TBD | 2029-04-30 | Preliminary Engineering | Exempt | 2027-07-01 | ISO Action | CAISO
1920-R-06 | Pardee-Sylmar 230 kV Line Rating Increase Project | SCE | 2019-2020 | 2023-06-01 | 2023-05-01 | 2023-06-23 | 2024-06-01 | 2024-06-01 | 2025-06-30 | 2025-06-01 | 2025-06-01 | 2025-06-25 | 2027-10-31 | 2027-10-31 | 2027-10-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | 2029-06-01 | Construction | Exempt | 2024-10-31 | No Change | N/A
2223-P-15 | San Bernardino-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 1931-04-01 | 2029-03-01 | 2031-12-31 | 2031-12-01 | 2031-12-01 | Engineering | Exempt | 2028-07-01 | No Change | N/A
2223-P-16 | San Bernardino-Vista 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2029-12-01 | 2029-03-01 | 2029-12-31 | 2031-12-01 | 2031-12-01 | Engineering | Exempt | 2028-01-01 | No Change | N/A
2425-R-21 | Serrano 230 kV SCD GIS Bus Split | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | 2033-10-28 | 2033-10-28 | Engineering | Exempt | 2033-01-10 | No Change | N/A
2223-R-20 | Serrano 4AA 500/230 kV Transformer Bank Addition | SCE | 2022-2023 | 2027 | N/A | New | New | New | New | New | New | Pending | Pending | 2027-12-30 | 2027-12-01 | 2027-12-01 | 2033-05-24 | 2033-05-24 | 2033-08-31 | Engineering | Exempt | 2030-08-01 | Material | Utility
2425-R-22 | Serrano 500 kV SCD Mitigation | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | 2033-08-29 | 2033-08-31 | Engineering | Exempt | 2033-01-10 | No Change | N/A
2223-P-17 | Serrano-Alberhill-Valley 500 kV 1 Line Upgrade | SCE | 2022-2023 | 2028 | N/A | New | New | New | New | New | New | Pending | Pending | 2028-12-31 | 2027-12-01 | 2027-12-01 | 2031-06-01 | 2031-08-29 | 2031-06-27 | Engineering | Exempt | 2030-08-01 | Bundling Dependency | Utility
2223-R-22 | Sylmar Transformer Replacement | SCE | 2022-2023 | 2026 | N/A | New | New | New | New | New | New | Pending | Pending | 2026-12-31 | 2026-12-01 | 2026-12-01 | 2028-01-07 | 2028-01-07 | 2028-01-07 | Engineering | Exempt | N/A | No Change | N/A | July 2026: Construction to be done by LADWP. Procurement only.
1718-R-11 | Tie line Phasor Measurement Units | SCE | 2017-2018 | 2020 | 2021-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-31 | 2025-12-01 | 2024-02-28 | 2024-02-05 | 2024-02-05 | 2024-02-05 | 2024-09-01 | Pending | 2025-12-31 | 2025-12-31 | TBD | TBD | Exempt | TBD | Other | Utility
2425-R-27 | Tortilla 115 kV Capacitor Replacement | SCE | 2024-2025 | 2029 | N/A | New | New | New | New | New | New | New | New | New | New | New | New | 2029-06-30 | 2029-06-01 | Preliminary Engineering | Exempt | 2028-10-04 | No Change | N/A
2526-P-04 | Trout Canton - Lugo 500 kV Line | SCE | 2025-2026 | 2035 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [6 empty] | July 2026: FERC 1000 Project, to be removed from TDFs.
2122-R-15 | Victor 230 kV Switchrack Reconfiguration | SCE | 2021-2022 | 2023 | N/A | New | Pending | Pending | Pending | 2025-04-01 | 2025-04-01 | 2025-04-30 | 2025-04-30 | 2025-04-30 | Pending | Pending | 2027-06-01 | 2027-06-09 | 2028-06-30 | Preliminary Engineering | Exempt | 2027-01-27 | Material | Utility | July 2026: Project ISD moved to account for major material procurement and construction sequencing with multiple on-going projects at Victor Substation
2223-P-21 | Vista-Etiwanda 230 kV 1 Line Upgrade | SCE | 2022-2023 | 2031 | N/A | New | New | New | New | New | New | Pending | Pending | 2031-12-31 | 2031-12-01 | 2029-03-01 | 2027-01-29 | 2027-06-01 | 2028-06-01 | Engineering | Exempt | 2026-10-01 | Material | Utility
2526-R-01 | Walnut 230 kV CB Upgrade | SCE | 2025-2026 | 2031 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-12-31 | Initiation | Exempt | 2030-10-01 | No Change | N/A

## SDGaE
TP Project ID | Project | PTO | Transmission Plan Approved | In-Service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
1112-R-27 | TL695B Japanese Mesa-Talega Tap Reconductor | SDG&E | 2011-2012 | 2016 | 2023-04-01 | 2023-02-01 | 2024-06-12 | 2024-12-17 | 2025-10-24 | 2023-02-13 | 2023-02-13 | 2026-02-24 | 2026-08-05 | 2026-08-01 | 2026-12-16 | 2027-05-12 | 2028-01-27 | 2028-01-26 | 2028-05-16 | 2029-03-21 | Design | 2016-04-25 | 2027-06-16 | Permitting (Non-CPUC/CEQA) | Agency - Federal
1213-R-32 | Sweetwater Reliability Enhancement | SDG&E | 2012-2013 | 2021-06-17 | 2027-12-01 | 2027-11-01 | 2027-06-01 | 2027-12-20 | 2027-12-20 | 2027-11-14 | 2027-11-14 | 2027-11-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2027-10-14 | 2026-07-16 | 2026-07-21 | 2027-03-15 | 2026-11-20 | Construction | Exempt | 2022-11-29 | Permitting (Non-CPUC/CEQA) | Utility
1314-R-24 | TL690E Stuart Tap-Las Pulgas 69 kV Sections Re-Conductor | SDG&E | 2013-2014 | 2015-06-01 | 2027-02-01 | 2026-11-01 | 2026-06-01 | 2026-03-30 | 2026-11-25 | 2026-11-10 | 2026-11-10 | 2026-12-09 | 2028-03-23 | 2028-03-16 | 2028-07-01 | 2028-05-03 | 2028-12-20 | 2029-06-08 | 2029-07-23 | 2030-04-17 | Design | Exempt | 2029-04-12 | Permitting (Non-CPUC/CEQA) | Agency - Federal
1415-R-07 | TL632 Granite Loop-In and TL6914 Reconfiguration | SDG&E | 2013-2014 | 2021-06-15 | 2024-12-01 | 2026-06-01 | 2028-06-01 | 2028-11-27 | 2026-05-13 | 2026-06-08 | 2026-06-08 | 2026-07-29 | 2026-08-10 | 2026-10-12 | 2026-12-21 | 2027-05-11 | 2027-03-31 | 2027-02-25 | 2027-02-15 | 2027-05-17 | Construction | 2025-01-30 | 2025-09-02 | Project Design | Utility
1718-R-09 | San Ysidro 69 kV Reconductoring (TL623C) | SDG&E | 2017-2018 | 2022-06-01 | N/A | 2029-02-01 |  |  | 2024-08-15 | 2029-02-27 | 2029-02-27 | 2029-04-30 | 2029-09-28 | 2029-12-04 | 1930-02-26 | 2029-07-27 | 2026-11-24 | 2027-04-19 | 2027-03-02 | 2027-04-05 | Design | Exempt | 2027-01-19 | Land Rights | Customer
2223-P-01 | 3 Ohm Series Reactor on Sycamore-Penasquitos 230 kV line | SDG&E | 2022-2023 | 2032 | N/A | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2026-10-01 | 2026-06-30 | 2027-07-16 | 2027-06-22 | Construction | Exempt | 2025-12-15
2223-P-08 | IV-North of Songs 500 kV line | SDG&E | 2022-2023 | 2034-06-01 | N/A | [13 empty] | 2032-01-01 | 2032-01-24 | Planning | 2026-11-26 | 2029-09-30
2223-P-13 | Rearrange TL23013 PQ-OT and TL6959 PQ-Mira Sorrento | SDG&E | 2022-2023 | 2032 | N/A | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2031-08-04 | 2032-03-25 | Design | TBD | 2031-08-19
2223-P-14 | Reconductor TL680C San Marcos-Melrose Tap | SDG&E | 2022-2023 | 2032 | N/A | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2031-09-01 | 2029-10-25 | Design | TBD | 2029-05-23
2223-P-19 | Upgrade on Hoodoo Wash-North Gila and Hassayampa-North Gila Transmission Lines | SDG&E | 2022-2023 | 2032 | N/A | 2032 | [12 empty] | 2032-05-01 | 2032-05-01 | Planning | N/A | TBD |  |  | Project and construction activities managed by APS
2223-P-20 | Upgrade TL13820 Sycamore-Chicarita 138 kV | SDG&E | 2022-2023 | 2032 | N/A | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2031-09-01 | 2029-04-18 | Design | TBD | 2026-10-30
2223-R-13 | Miguel-Sycamore Canyon (TL23021) 230 kV line Loop-in to Suncrest | SDG&E | 2022-2023 | 2032 | N/A | 2032 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2032-12-31 | 2032-01-06 | Design | Exempt | 2027-01-21
2223-R-13 | Miguel-Sycamore Canyon (TL23021) 230 kV line Loop-in to Suncrest | SDG&E | 2022-2023 | 2032 | N/A | 1905-07-24 | [6 empty] | TBD | 2032 | 2032 | 2032 | 2032 | 2032 | 2032-12-31 | 2030-05-23 | Design | 2026-05-08 | 2028-02-08
2324-R-19 | Valley Center System Improvement | SDG&E | 2023-2024 | 2028 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2028 | 2028 | 2030 | 2031-01-22 | 2030-02-15 | Design | 2027-04-05 | 2029-10-11 | Permitting (CPUC/CEQA) | Utility
2324-R-20 | Short Circuit Mitigation for Imperial Valley 230 kV Circuit Breakers | SDG&E | 2023-2024 | 2035 | N/A | [10 empty] | 2035 | 2035 | 2035 | 2035-10-02 | 2035-08-23 | Planning | 2028-10-17 | 2032-09-08 | Project Design | Utility
2324-R-21 | Short Circuit Mitigation for Miguel 230 kV Circuit Breakers | SDG&E | 2023-2024 | 2035 | N/A | [10 empty] | 2035 | 2035 | 2035 | 2028-02-21 | 2028-04-25 | Design | Exempt | 2027-07-16
2324-R-22 | SG and OT Redundant Bus Differential Relay | SDG&E | 2022-2023 | 2024 | N/A | 2024 | [6 empty] | TBD | 2024 | 2024 | 2032 | 2032 | 2025-12-31 | 2026-06-30 | 2026-09-30 | Construction | Exempt | 2026-08-30 | Workforce | Utility
2425-R-03 / 2425-R-04 | Coronado Island Reliability Reinforcement | SDG&E | 2024-2025 | 2027-08-30 | N/A | N/A | [11 empty] | N/A | N/A | 2028-08-17 | Design | 2026-06-19 | 2026-10-06 | Project Design | Utility
2425-R-06 | Sampson 69kV Overstressed Breaker Replacement | SDG&E | 2024-2025 | 2029-12-31 | N/A | N/A | [11 empty] | N/A | N/A | 2029-12-31 | Planning | Exempt | TBD
2425-R-06 | Vine Substation 230kV Expansion | SDG&E | 2024-2025 | 2029-12-31 | N/A | N/A | [11 empty] | N/A | N/A | 2029-12-31 | Planning | TBD | TBD
2526-R-24 | Penasquitos- Mira Sorrento 69KV #2 line | SDG&E | 2025-2026 | 2035 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2035-12-31 | Planning | TBD | TBD
2526-R-25 | TL600B Reconductor | SDG&E | 2025-2026 | 2035 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2035-12-31 | Planning | TBD | TBD
2526-R-26 | TL623C Reconductor | SDG&E | 2025-2026 | 2032 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2027-05-31 | Design | Exempt | TBD
2526-R-27 | TL690B & TL 697 Reconductor | SDG&E | 2025-2026 | 2031 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2031-12-31 | Planning | Exempt | 2030-01-01

## VEA_GLW
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
2223-P-02 | Beatty 230 kV Project | VEA/GLW | 2022-2023 | 2027-12-31 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2027-12-31 | 2028-05-31 | 2028-05-31 | 2028-05-31 | Permitting, engineering and design | N/A | 2027-03-01 | No Change | N/A | No change in ISD
2122-P-01 | GLW/VEA Area Upgrades | VEA/GLW | 2021-2022 (revised scope 2022-2023) | TBD |  | N/A | TBD | TBD | TBD | TBD | TBD | 2027-12-31 | 2027-12-31 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | Earliest June-27; latest Dec-27 | 2028-06-28 | 2028-06-28 | 2028-06-28 | Permitting, engineering and design | N/A | 2026-07-01 | No Change | N/A | No change in ISD
1718-R-11 | Tie line Phasor Measurement Units | VEA | 2017-2018 | 2020-12-01 | 2021-12-01 | 2022-12-20 | June-22 | 2022-12-20 |  | 2023-06-23 | 2023-09-23 | 2023-12-23 | 2023-12-23 | Q1/Q2-2024 | Q4/2024 | Q2/2025 | Q3/2025 | 2026-09-30 | 2026-09-30 | In Flight | N/A | 2026-09-26 | Unspecified | Telecommunication | Prior delay due to AT&T

## LSPower
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
1819-R-03 | Gates 500 kV Dynamic Voltage Support (Orchard Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2024-06-01 | 2025-01-01 | 2025-01-01 | 2025-01-25 | 2025-01-25 | 2025-03-25 | In-Service |  | In-Service | 2021-02-19 | 2023-04-01 |  |  | In-Service
2324-P-01 | Collinsville 230kV Reactor Project | LS Power | 2023-2024 | 2028 | [10 empty] | 2028-06-01 | 2028-06-01 | 2028-05-01 | 2028-12-28 | 2028-12-28 | Permitting | N/A | 2026 | No Change | N/A
2122-P-03 | Collinsville 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-05-01 | 2028-12-28 | 2028-12-28 | Permitting | Q3 2024 | 2026 | Permitting (CPUC/CEQA) | Agency - State
2122-P-04 | Manning 500/230 kV Substation Project | LS Power | 2021-2022 | 2028 | [6 empty] | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2027-12-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Construction | 2024-06-28 | 2026 | No Change | N/A | Construction in progress
1819-R-08 | Round Mountain 500 kV Dynamic Voltage Support (Fern Road Substation) | LS Power | 2018-2019 | 2024 | 2024-06-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | 2024-12-01 | TBD | TBD | TBD | 2026-03-26 | 2026-05-26 | 2026-07-01 | Construction | 2022-04-06 | 2024-03-25 | Outage | Utility | Construction in progress
2122-R-11 | San Jose Area HVDC 230 kV Line (Newark - NRS) | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-05-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | 2028-04-01 | Construction | 2024-05-17 | 2026 | No Change | N/A | Construction in progress
2122-R-10 | San Jose Area HVDC 500 kV Line (Metcalf – San Jose) | LS Power | 2021-2022 | 2028 | [6 empty] | 2028-04-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | 2028-05-01 | Construction | 2024-04-29 | 2026 | No Change | N/A | Construction in progress
2223-P-22 | SWIP-North 500kV Transmission Project | GBT | 2022-2023 | 2027 | [6 empty] | 2028-05-01: 2028-05-01; 2028-05-01: 2028-05-01; 2028-05-01: 2028-05-01; 2028-05-01: 2028-05-01 | Construction | N/A | 2026 | No Change | N/A | Construction in progress
2425-R-18 | Northern Receiving Station – San Jose B 230 kV Project | LS Power | 2024-2025 | 2030 | [6 empty] | 2028-05-01: N/A; 2028-05-01: 2030-05-01 | Permitting | Q2 2027 | 2028 | No Change | N/A
* LSPGC is LS Power Grid California, LLC, an LS Power affiliate that became a PTO on 3/12/25.
GBT is Great Basin Transmission, LLC, an LS Power affiliate that is the selected Project Sponsor for SWIP-North and is approved to become a PTO at energization.

## Lotus
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
2223-P-12 | North of Songs-Sorreno 500 kV Line | Lotus Infrastructure Global Operations | 2024 | 2032-01-01 | 2034-07-01 | 2032-01-01 | 2032-01-01 | 2032-01-01 |  | 2033-07-01 | Engineering | 2028-09-01 | 2029-10-01

## HWT
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2022-2023 Transmission Plan | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
2223-P-11 | North Gila–Imperial Valley 500 kV line | HWT | 2022-2023 | 2032-06-01 | 2032-06-01 | N/A | 2031-12-31 | 2031-12-31 | 2031-12-31 | 2031-12-31 | Permitting, engineering and design | 2025-09-02 | 2030-07-15 | No Change | N/A
2223-P-08 | IV-North of Songs 500 kV line and North of Songs Substation | HWT | 2022-2023 | 2034-06-01 | 2034-06-01 | N/A | 2032-10-19 | 2032-10-31 | 2032-10-31 | 2032-10-31 | Permitting, engineering and design | 2026-10-02 | 2030-12-23 | No Change | N/A

## CalGrid
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Previous In-Service July 2025 TDF | Previous In-Service Jan 2026 TDF | Current In-Service July 2026 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Reason for ISD Change from Original Comitted Date | Delay Resolver | Notes
2324-P-03 | New Humboldt 500 kV Substation with 500 kV line to Collinsville [HVDC operated as AC] | CalGrid | 2023-2024 | 2034-06-01 | N/A | N/A | N/A | 2034-06-01 | 2034-06-01 | Initial Development Activities | Q3 2027 | 2031 | No Change | N/A
2324-P-04 | New Humboldt to Fern Road 500 kV Line | CalGrid | 2023-2024 | 2034-06-01 | N/A | N/A | N/A | 2034-06-01 | 2034-06-01 | Initial Development Activities | Q3 2027 | 2031 | No Change | N/A

## CitizensEnergy
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Previous In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
1718-E-02 | IID S-Line Upgrade | Citizens Energy | 2017-2018 | 2021-12-01 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | Completed |  | 2023-07-21

## DCRT
TP Project ID | Project | PTO | Transmission Plan Approved | In-service Date at Approval in Transmission Plan | Expected In-Service Date 2020-2021 Transmission Plan | Previous In-Service Jan 2022 TDF | Previous In-Service Apr 2022 TDF | Previous In-Service Jul 2022 TDF | Previous In-Service Oct 2022 TDF | Previous In-Service Jan 2023 TDF | Previous In-Service Apr 2023 TDF | Previous In-Service Jul 2023 TDF | Previous In-Service Oct 2023 TDF | Previous In-Service Jan 2024 TDF | Previous In-Service July 2024 TDF | Current In-Service Jan 2025 TDF | Project Status | Expected CPUC Permit Application Filing | Expected Construction Start | Notes
1314-E-01 | Delaney-Colorado River 500 kV line | DCR Transmission | 2013-2014 | 2020 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-01 | 2024-04-24 | 2024-04-01 | 2024-04-24 | 2024-04-24 | 2024-05-24 | 2024-06-07 | 2024-06-07 | In-Service | Approved | 2022-10-22 | Energized 6/7/2024